## Slide 1: Community development department assessment, COST RECOVERY & FEE STUDY
LAKE COUNTY, CALIFORNIA
Notes: Drag an image from your computer. The dimensions must be at least 1920 x 1080 – preferably larger.

## Slide 2: THE MATRIX APPROACH
A fact-based, tailored approach built on 200+ community development and 400+ user fee studies and extensive California experience.
An experienced, dedicated in-house team with direct user fee, planning, engineering, and building operational expertise.
Extensive engagement with staff, customers, and stakeholders, including focus groups, surveys, and process mapping workshops.
A clear path to implementable solutions, with 85% of our recommendations enacted within three years.

## Slide 3: ORGANIZATIONAL & OPERATIONAL TASK PLAN
KICKOFF & INTERVIEWS
Project kickoff and conduct staff interview
PROCESS DIAGRAMMING
Workshops with staff to outline ”as is” process and develop process diagrams
TECHNOLOGY REVIEW
Assess current technology systems and functionality
CUSTOMER INPUT
Online survey and focus groups with recent development customers
COMPARISONS
Evaluate operations, process, technology, workload, organizational structure, housing/ economic development integration, etc.
CURRENT STATE PROFILE
Develop overview of current approaches, processes, and workload
EVALUATION & ANALYSIS
Best practices and comparative jurisdiction diagnostic assessment.
Draft and final reports will be compiled. Present findings to the County Board
REPORT & PRESENTATION

## Slide 4: FEE & COST RECOVERY TASK PLAN
DEVELOP FEE OVERVIEW
Review current fee schedule and approaches
TIME WORKSHOPS
Interview staff to understand time commitments by activity
HOURLY RATE DEV.
Develop fully burdened hourly rates
BENCHMARKING
Comparative survey to identify similar fees in other jurisdictions
DRAFT FEES
Develop draft and final fee study reports
TOTAL COST ANALYSIS
Determine full cost of providing development services by functional group
DRAFT & FINAL REPORT
Identify and revises fees based on work activity
Present fee study findings to the County Board
PRESENTATIONS

## Slide 5: PROJECT SCHEDULE
Work Program | Month 1 |  | Month 2 |  | Month 3 |  | Month 4 |  | Month 5 |  | Month 6 | 
PART A — ORGANIZATIONAL AND OPERATIONAL ASSESSMENT |  |  |  |  |  |  |  |  |  |  |  | 
Task A1 – Project Initiation & Staff Interviews |  |  |  |  |  |  |  |  |  |  |  | 
Task A2 – Diagram Operational Functions & Permitting Workflows |  |  |  |  |  |  |  |  |  |  |  | 
Task A3 – Technology & Systems Review |  |  |  |  |  |  |  |  |  |  |  | 
Task A4 – Current State Profile of Operations |  |  |  |  |  |  |  |  |  |  |  | 
Task A5 – Customer Service & Stakeholder Assessment |  |  |  |  |  |  |  |  |  |  |  | 
Task A6 – Benchmarking & Best Practices Assessment |  |  |  |  |  |  |  |  |  |  |  | 
Task A7 – Housing & Economic Development Integration Review |  |  |  |  |  |  |  |  |  |  |  | 
Task A8 – Evaluation, Analysis & Recommendations |  |  |  |  |  |  |  |  |  |  |  | 
Subtask 8a – Management Systems & Performance Effectiveness |  |  |  |  |  |  |  |  |  |  |  | 
Subtask 8b – Communication & Interdepartmental Coordination |  |  |  |  |  |  |  |  |  |  |  | 
Subtask 8c – Organizational Restructuring Options |  |  |  |  |  |  |  |  |  |  |  | 
Task A9 – Final Report & Presentation (Part A) |  |  |  |  |  |  |  |  |  |  |  | 
PART B — DEVELOPMENT FEE AND COST RECOVERY STUDY |  |  |  |  |  |  |  |  |  |  |  | 
Task B3 – Develop Schedule of Current & Potential Fees |  |  |  |  |  |  |  |  |  |  |  | 
Task B4 – Conduct Time Study Workshops |  |  |  |  |  |  |  |  |  |  |  | 
Task B5 – Develop Fully Burdened Hourly Rates |  |  |  |  |  |  |  |  |  |  |  | 
Task B6 – Perform Total Cost Analysis |  |  |  |  |  |  |  |  |  |  |  | 
Task B7 – Benchmarking Survey |  |  |  |  |  |  |  |  |  |  |  | 
Task B8 – Review & Revise Fee Study Results |  |  |  |  |  |  |  |  |  |  |  | 
Task B10 – Draft & Final Fee Study Report |  |  |  |  |  |  |  |  |  |  |  | 
Task B11 – Stakeholder Presentations |  |  |  |  |  |  |  |  |  |  |  |